# Broadband Equity, Access, and Deployment (BEAD) Program

# NEPA Project Area Review Process and Form

This review form assists BEAD Program subgrantees to evaluate their BEAD projects and potentially customize project areas that should move ahead as separate projects for National Environmental Policy Act (NEPA) review. Arizona Commerce Authority (ACA) will also use this form to document its review of the proposed smaller NEPA Project Areas.

## Overview

The National Telecommunications and Information Administration (NTIA) is the federal agency overseeing the BEAD program. It created the Environmental Screening and Permitting Tracking Tool (ESAPTT) to document the NEPA and permitting efforts for each BEAD project. ESAPTT will create one NEPA project area ID for each BEAD project ID. However, multiple NEPA project area IDs (also referred to as “NEPA Project Areas”) can be created and be associated with a single BEAD project ID. Since a single BEAD project may deploy broadband services to different geographic areas in Arizona, this geographic diversity may unnecessarily expand the scope of the NEPA review, complicating and potentially delaying approval for projects that would have independent functionality. As there are potential benefits and drawbacks for BEAD project deployment by creating multiple NEPA Project Areas for a single BEAD project ID, it is important that subgrantees review this form and consider potential benefits and drawbacks:

## Potential Benefits of Segmentation to Consider:

- Accelerating Deployment: Areas without environmental constraints can receive NEPA approval and begin construction sooner, rather than waiting for reviews in other parts of your project.

- Meeting Deadlines: Begin serving customers in ready areas while consultations continue elsewhere, helping you meet BEAD deployment deadlines.

## Potential Drawbacks of Segmentation to Consider:

- Increasing Costs: Each NEPA Project Area requires separate environmental review documentation, potentially increasing consultant fees.

- Creating Administrative Burden: Managing multiple NEPA reviews means tracking multiple timelines, submissions, and approval processes with NTIA and other regulatory agencies.

- Adding Deployment Inefficiencies: Small NEPA Project Areas may not justify the additional cost of mobilizing and commencing deployment activities.

## Updated Project Description Requirements

NTIA also issued new project description standards that must be followed for all NEPA submissions and included in the NEPA Project Area csv file submitted to NTIA. Please review NTIA's Sample ESAPTT Project Maps and Descriptions guidance file and “project_description” row in Table 1 for further instructions on how to update the Project description with additional information including technology type, infrastructure details, and deployment methods.

## Review Process

The review process documented in this form offers subgrantees an opportunity to divide their BEAD projects into separate NEPA Project Areas, potentially allowing some NEPA Project Areas to move ahead and be approved sooner than others. This review form is meant to assist in verifying that:

- Each NEPA Project Area has Independent Utility. This means the project can provide service on its own, without needing other parts of the overall BEAD project to be built first. It must deliver a real, usable service improvement to end-users independently.

- Each NEPA Project Area has NOT been improperly segmented. This means you haven't split the BEAD project into smaller NEPA Project Areas just to avoid a more detailed NEPA review. Any division into multiple NEPA Project Areas must be based on clear operational reasons, not to bypass a more thorough analysis (like breaking a project into smaller parts to qualify for a Categorical Exclusion when an Environmental Assessment would normally be needed).

- Subgrantees who do not want to identify separate NEPA Project Areas for their BEAD projects should simply notify ACA. They do not need to follow these steps or fill out this review form.

# Steps for Identifying NEPA Project Areas

Subgrantees should follow these steps to identify the smaller NEPA Project Areas:

- Use NTIA’s ArcGIS Pro Permitting and Environmental Information Tool (APPEIT) (APPEIT user guide) and ACA’s Arizona Permit Finder to evaluate the overall BEAD project area. Both online tools will generate reports that highlight potential issues that could delay the NEPA process, such as the presence of federal land or the presence of critical habitat for a threatened or endangered species.

- Based on the evaluation results, identify one or more separate NEPA Project Areas that would have independent utility and could move through the NEPA review process more quickly than the area with issues that could be delayed due to the issuance of a NEPA decision.

- Once the separate NEPA Project Areas are identified, use the APPEIT and Arizona Permit Finder online tools to evaluate each NEPA Project Area to verify the assumption that the project could potentially be accelerated.

- Fill out the form at the end of this guidance to document the evaluation results.

# Documentation to Submit for Review of NEPA Project Areas

Subgrantees should submit the following documentation to ACA for review of the proposed NEPA Project Areas:

- NTIA APPEIT report and ACA Arizona Permit Finder report for original BEAD-awarded project area

- Shapefiles for proposed NEPA Project Areas that define the geographic boundaries of your proposed NEPA Project Areas

- NTIA APPEIT reports and ACA Arizona Permit Finder reports for each proposed NEPA Project Area, respectively

- Completed NEPA Project Area Review Form (at the end of this guidance) for each NEPA Project Area (subgrantee to complete middle column of form), respectively

- Completed “NEPA_Project_id_Completed_[PROJECT NAME].csv” file including subgrantee inputs in the column titled, “NEPA_project_id” for each “location_id” indicating the assigned NEPA Project Area, respectively, and updated “project_description.” Table 1 below describes the required information.

Table 1

| Column | Column title | Description |
| --- | --- | --- |
| A | location_id | Location ID number assigned to BEAD project (refer to the “fp_locations.csv” file from the BEAD Final Proposal) |
| B | project_id | BEAD project ID number (refer to the “fp_locations.csv” file from the BEAD Final Proposal) |
| C | technology | Broadband technology code |
| D | project_name | Project name (refer to the “fp_deployment_projects.csv” file from the BEAD Final Proposal) |
| E | project_description | Project description (up to 1,000 characters, describing infrastructure elements and activities subject to environmental review, including number of locations to be served, technology type, deployment method, and relevant contextual information) See examples below: Sample ESAPTT Project Description Summary (Buried Fiber) Installation of 58 miles of buried fiber optic cable in a previously disturbed, existing road right-of-way along Route 42 from Dalton to Marysville to serve 35 residences in Whitefield and Murray Counties, Example State. Sample ESAPTT Project Description Summary (Tower Project) Construction of two monopole and two lattice communication towers to serve 240 residences between Willows City and Copper City, in New County, Example State. Subgrantee updates data in this column |
| F | uei | Unique Entity Identifier (UEI) number (refer to the “fp_deployment_projects.csv” file from the BEAD Final Proposal) |
| G | cai | Community Anchor Institution (CAI) presence, as applicable (denotes if an entry is a CAI) |
| H | md5pkeyhash | Unique identifier for CAIs, utilized in the subgrantee portal. |
| I | latitude | Latitude |
| J | longitude | Longitude |
| K | NEPA_project_id | The BEAD project ID number with a hyphen and N1, N2, etc. added at the end – Subgrantee inputs data in this column |

Figure 1 below shows entries for an example project.

Figure 1

# NEPA Project Areas Review Submission and Next Steps

Subgrantees will complete the NEPA Project Areas workflow in the BEAD Grantor Portal and submit the five (5) completed sets of documents listed above to ACA for review by January 22, 2026 and prepare for follow-ups from ACA and its consultant team.

If you have any questions, please reach out to ACA via the Ready platform or the ACA Permitting Mailbox at beadpermitting@azcommerce.com.

# NEPA Project Area Review Form

Subgrantees should complete this form for each proposed NEPA Project Area.

| Subgrantee |  |
| --- | --- |
| BEAD Project Name |  |
| BEAD Project ID |  |
| Proposed NEPA Project ID |  |
| Date Review Form Completed |  |
| EHP Consultant/Staff Name and Organization |  |
| EHP Consultant/Staff Email and Phone Number |  |

| Question/Topic | Subgrantee Response | ACA Review Comment |
| --- | --- | --- |
| Was the NEPA Project Area shapefile provided by the subgrantee? | Yes ☐ No ☐ |  |
| Was the APPEIT report provided by the subgrantee? | Yes ☐ No ☐ |  |
| Was the Arizona Permit Finder report provided by the subgrantee? | Yes ☐ No ☐ |  |
| Is independent utility confirmed by subgrantee? | Yes ☐ No ☐ |  |
| Does the subgrantee affirm that improper segmentation has not occurred? | Yes ☐ No ☐ |  |
| Does the project intersect with federal land? | Yes ☐ No ☐ If yes, describe: |  |
| Does the project intersect tribal land or tribal trust or treaty lands? | Yes ☐ No ☐ If yes, describe: |  |
| What potential state permitting agencies have been identified in the project area? | Provide a list: |  |
| Does the project area have any known sites listed, or eligible for listing, on the National Register of Historic Places? | Yes ☐ No ☐ If yes, describe: |  |
| Does the project area have critical habitat for threatened or endangered species that may be affected? | Yes ☐ No ☐ If yes, describe: |  |
| Does the project area have waters of the United States, including wetlands, that may be affected? | Yes ☐ No ☐ If yes, describe: |  |
| Does the project area have any floodplains or Federal Emergency Management Agency Flood Hazard Zones that may be affected? | Yes ☐ No ☐ If yes, describe: |  |
| Does the project area contain any hazardous materials sites, impaired waters, sole-source aquifers, or Clean Air Act non-conforming areas? | Yes ☐ No ☐ If yes, describe: |  |
| Does the project area have power lines, railroads, or other infrastructure that may be affected? | Yes ☐ No ☐ If yes, describe: |  |
| Does the project area have any other unique issue that may not be listed above? | Yes ☐ No ☐ If yes, describe: |  |

https://broadbandusa.ntia.gov/sites/default/files/2026-01/DOC_NTIA_Sample_ESAPTT_Project_Maps_and_Descriptions_01_26.pdf

https://nbam.ntia.gov/content/37fa42c6313e4bdb9d8a9c05d2624891/about

https://broadbandusa.ntia.gov/sites/default/files/2025-04/NBAM_APPEIT_User_Guide.pdf

https://experience.arcgis.com/experience/8ae6e9631c4c4d4baceeb26918dc1cb4/

Independent utility means the project can provide service on its own, without needing other parts of the overall project to be built first. It must deliver a real, usable service improvement to end-users independently.

Improper segmentation means you haven't split the project into smaller NEPA Project Areas just to avoid a more detailed NEPA review. Any division into multiple NEPA Project Areas must be based on clear operational reasons, not to bypass a more thorough analysis (like breaking a project into smaller parts to qualify for a Categorical Exclusion when an Environmental Assessment would normally be needed).